Developing and Implementing Regional Action Plans for Persons with Disabilities:

Lessons from Aceh and East Nusa Tenggara

Lessons Learned

September 2025

# Executive Summary

This brief is for planners, national and subnational policymakers, civil society organisations (CSOs), academics, and other development partners involved in designing inclusive policies and development plans for persons with disabilities.

This document summarises the lessons learned from developing the Regional Action Plan for Persons with Disabilities (RAD PD) in the provinces of Aceh and East Nusa Tenggara (Nusa Tenggara Timur/NTT), supported by the SKALA Program. SKALA’s experience identified six key factors that influence the effectiveness of RAD PD development and use: (1) strong leadership and political commitment, demonstrated through annual budgets and measurable indicators; (2) collaborative, cross-sectoral consultations; (3) sound disability data governance to ensure regular updates, sharing, and utilisation; (4) disability-inclusive planning, with the systematic involvement of persons with disabilities throughout the planning cycle; (5) the capacity of the RAD PD Drafting Team and government offices to adopt disability-inclusive planning; and (6) a robust strategy for outreach and monitoring and evaluation (M&E) to ensure effective utilisation of the RAD PD.

1

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

2

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

Based on these lessons, SKALA has proposed eight steps to strengthen the RAD PD process and its outcomes.

- Ensure the meaningful participation of persons with disabilities.

- Equip the Drafting Team, government offices (OPDs), organisations of persons with disabilities (OPDis), CSOs, academics, and other development partners with appropriate knowledge and analytical tools.

- Develop a system that collects accurate, disaggregated disability data that can be used across sectors.

- Strengthen collaboration through the active participation of stakeholders.

- Align the RAD PD with regional planning and budgeting documents.

- Design measurable, inclusive, and systematic strategies for the utilisation, monitoring and evaluation of the RAD PD, involving OPDis.

- Establish a Disability Thematic Forum at provincial and regency/city levels to provide a cross-sectoral platform for OPDs, OPDis, academics, CSOs, the media, and development partners.

- Promote an inclusive budget tagging system to support the monitoring and evaluation of program and activity implementation.

These lessons and recommendations serve as a reference for local governments to help them further develop and implement RAD PD effectively.

3

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

Context:

# RAD PD as a Driver of Inclusive Development and SKALA’s Role

Indonesia’s 2025-2029 National Medium-Term Development Plan (RPJMN) lays a strong policy foundation for promoting gender equality and empowering women, youth and persons with disabilities through gender mainstreaming and social inclusion (PUGIS).1

This is consistent with Indonesia’s commitment to guarantee the rights of persons with disabilities, as outlined in Law No. 8 of 2016 on Persons with Disabilities and Government Regulation No. 70 of 2019. To implement these policies, the government issued Regulation No. 3 of 2021 from the Ministry of National Development Planning (Bappenas), which requires the preparation of the Regional Action Plan for Persons with Disabilities (RAD PD). As the main reference document for inclusive regional development, the RAD PD ensures that development not only fulfils rights but also empowers persons with disabilities as active participants. The document also serves as a key instrument to advance inclusive development by ensuring access to facilities, services, and information.

In Aceh and NTT, SKALA played a strategic role in ensuring that RAD PD processes and results were evidence-based, inclusive, collaborative, effective, and well targeted. In Aceh, SKALA facilitated cross-sector collaboration and advocated with provincial and regency/ city governments, CSOs, and national ministries. SKALA also provided substantive input at each stage and worked to ensure the full participation of persons with disabilities in policy formulation, budgeting, and implementation.

In NTT, SKALA provided technical guidance on Access, Participation, Control, and Benefit (APKM) analysis, the RAD PD process, matrix completion, and the identification of issues and needs of persons with disabilities. SKALA also helped the Drafting Team formulate documents, including the use of an apportionment approach to estimate budget requirements based on the proportion of persons with disabilities in the total population.

¹ This strategy ensures that women, men, persons with disabilities, the elderly, indigenous peoples and other vulnerable groups have equal opportunities to participate meaningfully in development processes and benefit from their outcomes (see Presidential Regulation Number 12/2025; RPJMN 2025-2029 Narrative, p.81; Bappenas 2025).

4

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

Lessons:

# RAD PD Formulation in the Provinces of Aceh and NTT

The formulation and use of RAD PD in these provinces show distinct characteristics, which are influenced by stakeholder preparedness, institutional dynamics, and data availability. The table and narrative below outline the approaches adopted in both provinces and highlight key lessons learned from their experiences.

Table 1 – Formulation of RAD PD in Aceh and NTT

| Aspect | Aceh | NTT |
| --- | --- | --- |
| Initiator | Top-down approach, driven by central government directives | Bottom-up approach, initiated by OPDis and CSOs, and later adopted by the regional head |
| Drafting Team | Academics from Syiah Kuala University and UIN Ar-Raniry, Social Affairs Office, Bappeda; OPDis involved only at the final consultation stage | Joint team of OPDs, academics, and OPDis, with OPDis involved from the start of the drafting process |
| Involvement of Organisations of Persons with Disabilities | Limited to the final stage | Included from the beginning, although not yet fully optimal |
| Data Sources | Social Affairs Office, Aceh Population Registration Office, and Statistics Indonesia (BPS); data not updated regularly | Multiple sources (including CSOs and OPDis); data not updated regularly |
| Innovation | - | Addition of a chapter on gap analysis and the apportioning approach |
| Use | Campaigns and greater awareness of disability issues; additional initiatives at UIN and regency/city levels; accelerated progress in drafting the Qanun (Local Regulation) on Disability | Already integrated into Long-Term Development Plan (RPJPD) and with a format prepared for Medium-Term Development Plan (RPJMD); adopted by Social Affairs and Education Offices |

Lesson 1:

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

5

# Leadership and Political Commitment as the Foundation

Effective RAD PD formulation requires leadership and political commitment from local leaders. SKALA’s experience in Aceh and NTT shows that national regulations and technical support alone are not enough. Local leaders can mobilise bureaucratic elements, ensure the involvement of OPDis, and integrate RAD PD into the development agenda.

- In Aceh, the Head of the Regional Development Planning Agency (Bappeda) led the RAD PD development process, coordinating government offices at the provincial and regency/city levels and working with development partners and CSOs. The process began in January 2023 with the formation of a coordination team, technical preparation, an analysis of the situation of persons with disabilities, and focused group discussions with ten districts and cities. Once the draft document was finalised, a draft Governor’s Regulation was prepared and subsequently enacted as Governor’s Regulation No. 53 of 2023 on the RAD PD for the period 2024–2029. The Head of Bappeda provided consistent leadership throughout the process, supported by the Regional Secretary, who directed the Drafting Team. This team was co-led by the Head of Bappeda and the Head of the Special Development Planning Division, and included three academics from local universities as lead authors.

- In NTT, the Governor demonstrated his political commitment by appointing civil servants with disabilities as special staff and commissioning a Disability Profile in 2019 that identified eighteen OPDis as strategic government partners. In the same year, the Regional Development Planning, Research, and Innovation Agency (Bapperida) developed the RAD PD with full funding from the Regional Budget (APBD). This document was approved in 2019 and reinforced by Governor’s Regulation No. 68 of 2020 on the Protection and Fulfilment of the Rights of Persons with Disabilities. The NTT Provincial Government later aligned the document with national guidelines through a revision supported by Regional Regulation No. 6 of 2022 on the Empowerment and Fulfilment of the Rights of Persons with Disabilities.

Lesson 2:

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

6

# Cross-Sector Consultative Process for an Evidence-Based RAD PD

The RAD PD formulation process requires a collaborative approach involving multiple stakeholders from the outset. A cross-sector consultative process strengthens the legitimacy of the document and ensures that the plan responds to local needs and can be implemented effectively.

- In Aceh, Bappeda led consultations with ten regency and city governments, provincial OPDs, OPDis, CSOs, and academics. Academics from Syiah Kuala University and UIN Ar-Raniry also contributed to the situation analysis and drafting of the document. During the finalisation stage, the SKALA Program and the Faculty of Da’wah and Communication at UIN Ar-Raniry provided inputs that further strengthened the document. This collaboration produced a contextual and data- driven document that reflected aspirations across different levels of government and generated relevant sector-specific strategies. Other significant contributing factors included funding from the provincial government, a well-structured work plan, and technical guidance from Bappenas.

- In NTT, Bapperida established a Drafting Team comprising OPDs and OPDis, which partnered with the INKLUSI Program -including the Disability Advocacy Transformation Movement for Inclusion (GARAMIN) and the Indonesian Blind Association (Pertuni) of Kupang City- and academics from the Agricultural Polytechnic of Nusa Cendana University. The AIPJ and SKALA Programs, together with Bappenas, enhanced the process by providing additional expertise and support. This collaborative effort resulted in the formation of a Provincial Coordination Team, formalised through a Governor’s Decree in 2023. This team brings together OPDs, OPDis and disability groups from villages in two regencies.

Lesson 3:

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

7

# Strengthening Disaggregated Disability Data for Better Analysis

RAD PD can support inclusive planning when it is supported by complete and up-to-date disability data. Data is fundamental to analysing the gaps in access, participation, control, and benefits experienced by persons with disabilities. With better data, the government can develop a better understanding of the problems and relevant programs to close those gaps. SKALA’s experience in two provinces revealed issues in the governance of disability data in terms of its availability, accuracy, and use.

- In Aceh, the formulation of the RAD PD relied on baseline data from the Social Affairs Office. This data included the number and proportion of persons with disabilities in each regency and city, disaggregated by gender, type of disability, and age. This data served as an important starting point, but it was insufficient to capture the full complexity of the situation and needs of persons with disabilities. The Drafting Team and reviewers acknowledged that a lack of detailed data and depth of situation analysis could obscure the intended policy direction. At the same time, national guidelines emphasise the importance of identifying the barriers, potential and needs of persons with disabilities as the basis for RAD PD formulation.

- In NTT, efforts to provide disaggregated disability data were inconsistent, particularly with regard to ensuring availability by gender and age. Access to more comprehensive Regsosek data was only obtained in May 2024, which limited its use in the RAD PD process. In addition to data from the Social Affairs Office, the NTT RAD PD also sourced data from other technical offices, the Population Census, the General Election Commission (KPU), and OPDis. However, the scope and quality of this data remained limited. Much of it was only available at regency level, was not collected regularly, and was not structured to support planning. For example, data from OPDis was prepared for programs at regency/district level and was therefore not representative enough to serve as a basis for a strategic policy document at provincial level.

Overall, gaps in the availability and quality of disability data from different sources weakened the RAD PD analysis and hindered its integration into regional planning and budgeting documents.

Lesson 4:

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

8

# Disability-Inclusive Planning Processes for Effective Policies

To ensure the plan is relevant, applicable and responsive to the needs of persons with disabilities, it is imperative to involve OPDis from the outset of RAD PD formulation. Meaningful participation requires strong organisational capacity, equal representation, and sufficient technical support. In both Aceh and NTT, OPDis participated in the formulation process, but their involvement was ad hoc rather than intentional and systematically embedded throughout the policy cycle.

- In Aceh, OPDis involvement has not been optimal as this was not guaranteed from the outset. A limited understanding of the issue, weak internal preparedness, and a lack of opportunities to participate have prevented OPDis from contributing to data validation and policy direction. Consequently, the RAD PD analysis remains normative and fails to reflect real needs. In the health sector, for example, the main challenges include the absence of Minimum Service Standards (SPM) for persons with disabilities, limited access to services, and a shortage of qualified healthcare professionals. However, the activities listed in the plan focus more on general efforts, such as sign language training, the provision of inclusive facilities, health education, disability exercise programs and campaigns to increase vegetable consumption.

- In NTT, OPDs collaborated with eighteen OPDis to prepare the strategic target and gap matrices. Each target had one planning staff member and one OPDis representative as facilitators. This arrangement strengthened the analysis of disability gaps and needs. However, as most OPDis operate at regency/city level, their contributions were often less relevant to provincial-level policy. They were also only involved in preparing the gap and strategic target matrices, so they lacked the capacity and understanding to contribute to provincial policies and programs. Accessibility barriers posed further challenges, including a shortage of sign language interpreters and materials not adapted for all types of disability, which restricted full participation. Consequently, although the document addressed some issues, most activities and sub-activities did not directly target persons with disabilities.

Lesson 5:

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

9

# The Capacity of the Drafting Team Determines Policy Direction and Quality

The Drafting Team’s understanding of disability issues and ability to articulate them in planning documents shape both the policy direction and the overall depth and quality of the RAD PD. In both provinces, OPDs represented in the Drafting Team required stronger support in disability-focused policy analysis skills to effectively translate inputs into standard planning formats.

- In Aceh, the Drafting Team encountered difficulties in responding to suggestions from OPDis that were beyond the authority of the provincial government. Most of these suggestions related to basic services, such as social assistance, health and housing, which are the responsibility of regency/city governments. The team also struggled to translate recommendations into program and activity terminology that complied with planning requirements. Consequently, many sections of the RAD PD matrix were normative and lacked adequate data support and specificity. Several of the indicators used were also not aligned with national guidelines and did not adhere to the SMART principles (Specific, Measurable, Achievable, Relevant and Time-bound).

- In NTT, the 2019 drafting process had to be redone because it did not comply with the new national guidelines issued in 2021. A lack of technical assistance from the central government further slowed the process. Even after revision, similar challenges persisted because only a small proportion of activities and sub-activities were specifically targeted at persons with disabilities. Technical support was crucial in improving the effectiveness of the RAD PD. For example, SKALA introduced an apportioning approach that encouraged the addition of a gap analysis chapter to the RAD PD matrix. This significantly reduced the estimated budget requirement from around Rp5.93 trillion to Rp9.08 billion.

10

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

Lesson 6:

# Strategic and Targeted Dissemination to Promote RAD PD Use

Once enacted, the RAD PD document must be disseminated systematically and inclusively to ensure broad understanding and effective utilisation.

- In Aceh, the Governor’s Regulation on RAD PD provided a legal basis for dissemination, but it reached only a limited number of OPDs and OPDis. A more targeted approach is required to extend dissemination beyond the Drafting Team staff to government offices, OPDis, the Aceh Provincial Parliament, local governments, village leaders, and development partners. Outreach materials must be adapted to the needs of different stakeholders, with sign language and simplified summaries provided for persons with disabilities and supported by a clear communication plan.

- In NTT, the Governor’s Regulation on RAD PD was enacted on 30 September 2024. However, OPDis and OPDs still have limited understanding of its content. Some OPDis have shared information within their networks, but these efforts have been partial and uncoordinated. OPDis have proposed to simplify the document and provide it in accessible versions. They also suggest that dissemination be complemented with training on technical terminology to better support their upcoming advocacy efforts.

Table 2 – Applying RAD PD in Practice

| Aceh | NTT |
| --- | --- |
| Effects of the RAD PD process: Encouraged public discourse, cross-sector action, and inclusive initiatives that go beyond the content of the document. | Initial use of RAD PD in long-term planning: Although enacted after the 2025 planning cycle, RAD PD has begun to be integrated into the RPJPD 2025–2045. |
| Inclusive campus initiative: UIN Ar-Raniry established a disability service unit, opened scholarships through the Islamic Trust Fund, and introduced a course on inclusive education. | Integration by Bappeda: A specific format is being prepared to incorporate RAD PD into the RPJMD. |
| Replication by other regions: Regencies/cities such as North Aceh began to prepare Disability Action Plans after participating in the provincial RAD PD consultation. | Sectoral implementation in OPDs: The Social Affairs Office and Education Office have carried out inclusive programmes, such as procuring learning aids and providing residential services in line with SPM indicators. |
| Improved public services: Ramps made available at the Grand Mosque, sign language interpreters in places of worship, and discounted transport and tourism fees for persons with disabilities. |  |
| Accelerated regulation: The Disability Qanun, initially targeted for completion in 2026, was issued in April 2025. |  |

11

Developing and Implementing Regional Action Plans for Persons with Disabilities: Lessons from Aceh and East Nusa Tenggara

Recommendations and Conclusion

SKALA’s support for the RAD PD formulation in Aceh and NTT resulted in eight recommendations to strengthen the quality and impact of the plan.

- Ensure the systematic and meaningful involvement of persons with disabilities OPDis should be involved from the outset of the process, from the situation analysis to the validation stage. Reasonable accommodation must be provided to enable them to contribute meaningfully.

- Strengthen the capacity of drafting teams, OPDis, OPDs, CSOs and academics Teams need a stronger understanding of rights-based approaches, the use of disaggregated data and planning principles such as SMART. Training and technical assistance are critical to producing sharper, more operational documents.

- Develop a system that collects accurate, disaggregated disability data that can be used across sectors Reliable data is the basis for robust situation analysis and effective policymaking. Data collection, updating, and use must become an integral part of regional planning, as limited data continues to undermine the effectiveness of RAD PD.

- Facilitate consistent collaboration between all stakeholders throughout the process RAD PD Coordination Teams can serve as forums in which OPDs, OPDis, academics and development partners can share perspectives, strengthen commitment and take ownership of the plan.

- Align RAD PD with subnational planning and budgeting documents The RAD PD should follow the structure and cycles of long-term development plan (RPJPD), medium-term development plan (RPJMD), annual work plan (RKPD), and OPD strategic plans (Renstra). This alignment ensures that RAD PD informs programs and budget allocations.

- Design clear, measurable and inclusive strategies for the use, monitoring and evaluation of the RAD PD, involving OPDis These strategies should be developed from the outset and include OPDs, OPDis, academics, and development partners. They should ensure that RAD PD is integrated into other strategic documents and connected to initiatives that improve basic services for persons with disabilities. Activities must also be available in accessible formats, including simplified versions and training for OPDis on technical terms.

- Establish Disability Thematic Forums at provincial and regency/city levels These forums should bring together OPDis, local governments, academics, CSOs, the media, and development partners to regularly review the implementation of RAD PD.

- Introduce inclusive budget tagging in the Regional Government Information System (SIPD) Currently, SIPD lacks disability-related budget tagging. This mechanism is important to make monitoring, reporting, classification, and evaluation of spending easier and more transparent.

The effectiveness of RAD PD formulation and implementation relies on strong coordination, cross- sector collaboration, meaningful involvement of OPDis, reliable data, committed local leadership, and technical support. These fundamentals ensure that the RAD PD is not only implemented and budgeted but also delivers improvements for persons with disabilities.

Website SKALA:

WA Channel SKALA:

IFC Tower 2, Level 17

Jl. Jendral Sudirman Kav. 22-23 Jakarta 12920 skala.or.id	info@skala.or.id